## Slide 1
nBLM SYSTEM STATUS
Laura Segui
(laura.segui@cea.fr)
21/11/2017
4th ESS BI Forum

## Slide 2: OUTLOOK
nBLM
Detector
Gas System
FEE
BEE and Control System

## Slide 3: OUTLOOK
nBLM
Detector
Gas System
FEE
BEE and Control System
New Mechanics
Tests planned
Distribution and installation in ESS
General update
Dedicated talk by Y. Mariette
Dedicated talk by P. Legou

## Slide 4: Motivation
nBLM  neutron Beam Loss Monitoring system based on the detection of fast neutrons with Micromegas detectors. + low sensitivity to gammas and X-Rays.
Objective: Protection + monitoring normal operation
  To maintain accelerator activation at a low level (loss << 1 W/m)
  For fine beam tuning purpose, particularly for high beam intensity
  Machine Protection
Project to deliver and commission 42 modules (84 detectors) by April 2019
To be installed mainly in the DTL and Spokes regions: Eproton 3.6 – 216 MeV
  Some will be tested also at higher energies
Why new BLM?
  Complementary to the others ESS BLM systems
  At low beam energy only neutrons and photons can escape beam pipe
  Photons :
    X-rays and γ’s are highly produced by the RFQ and superconductive cavities
    Impossible to distinguish contributions coming from beam or RF…
  Neutrons :
    Thermal neutrons: no loss locations
    Fast neutrons: good for beam loss representation
L. Segui 21/11/2017 – 4th ESS-BI Forum 1
BLM insensitive to thermal n’s
BLM insensitive to photons

## Slide 5: PROJECt planning
Dec. 2017: CDR1.1
Jun 2017: PDR1.2 Start prototype tests
Dec 2016: PDR1.1
Oct 2018:
SAR vertical integration test
April 2018: CDR1.2 (Final)
ESS commissioning 2019
 Juillet 2016: kick-off meeting
 Déc. 2016: PDR1.1
  First design of the prototype
  MC studies
July 2017: Final PDR + 1st prototypes tests
Dec. 2017 CDR1.2 + new detector design
Nov 2017 – Avril 2018 tests at different radiation facilities
Avril 2018: CDR1.2 Final
Avril-Oct 2018: Detector production and QA/QC
System delivered to ESS Nov. 2018
ESS hand over: April 2019
L. Segui 21/11/2017 – 4th ESS-BI Forum 2

## Slide 6: nBLM Detectors
Two types of detectors: slow and fast
    Different physical reaction to create the charged particles from the neutrons
    Different applications
L. Segui 21/11/2017 – 4th ESS-BI Forum 3
 | SLOW | FAST
Convertor | B4C | Mylar or Polypropylene
Reaction | (n,α)10B | (n,p)
Signal | Fast neutrons after moderation | Fast neutrons
Detected energy | ~constant | Continuum distribution of energies
Sensitivity | 10-6 < En < 100 MeV | En > 0.5 MeV
Solid angle | 4π | 2π, n coming from the front only
Efficiency | ~few n·cm-2·s-1 | ~10-100 times smaller
Response time | ~200µs | ~0.01µs
Objective | Monitoring of small losses | Alarm (in 5 µs) Fine structure of the lost
Shielding | Yes, for thermal neutrons | Not needed

## Slide 7: nBLM Detectors
Borated rubber (1mm)
Polyethylene (4cm)
Aluminium chamber
B4C deposited on Al
He+CO2 gas
MMs detector
n,
γ
Polyethylene moderator
Two types of detectors: slow and fast
SLOW
Absorber shielding
Detection of fast neutrons after moderation in polyethylene (~4cm)
Gas chamber with layer of B4C
  (n, α) 10B reaction
More efficient, 4π, but slower response
FAST
Recoil protons produced by neutrons in polypropylene
High flux high energy n's (>0.1 MeV)
Faster response
Just the gas chamber with polypropylene at the cathode
Aluminium chamber
Plastic deposited on Al
He+CO2 gas
MMs detector
n,
γ
L. Segui 21/11/2017 – 4th ESS-BI Forum 4

## Slide 8: nBLM Detectors
Two types of detectors: slow and fast
SLOW
Absorber shielding
Detection of fast neutrons after moderation in polyethylene (~4cm)
Gas chamber with layer of B4C
  (n, α) 10B reaction
More efficient, 4π, but slower response
FAST
Recoil protons produced by neutrons in polypropylene
High flux high energy n's (>0.1 MeV)
Faster response
Just the gas chamber with polypropylene at the cathode
L. Segui 21/11/2017 – 4th ESS-BI Forum 4

## Slide 9: nBLM Detectors
L. Segui 21/11/2017 – 4th ESS-BI Forum 5
Mezzanine card
New
Design
Old Design
Signal, HV, LV, gas connectors
New detectors design
New mechanics to improve electronic shielding
  More compact, easier for installation, more “industrialized”
  All connections in front
  Same mechanics for fast /slow
New electronics: mezzanine cards
  One for signals + PAs; another for HV
  Fastr replacement
  Easier to test different options  no need to change detector
  More details in Philippe’s talk
Design of closed gas recirculation system via an oxisorb filter
  Needed for tests at LINAC 4

## Slide 10
nBLM Detectors – new design

## Slide 11: New Detector production
Mechanics
Initially construct 4 chambers  for Dec 2017
When finalized, ~90 chambers
Production to start in ~June 2018
Micromegas
3x3 detectors per PCB (hopefully!)
2 boards initially  for Dec 2017 – Jan. 2018
10-12 boards by June 2018
Bulking at DEDIP lab
Pre-series production to start immediately
FEE + HV boards
Design done (more details in Philippe’s talk)
First boards will be ordered soon
Gherber for 3x3 MMs board
L. Segui 21/11/2017 – 4th ESS-BI Forum 6
Actual design with electronics on-board. The detector itself does not change

## Slide 12: nBLM PLAnned TESTS
Test Facility | Particle | Test | Date
Birmingham MC40 | Protons to material target | - Response under different loss scenarios - Electronics ageing | Nov-17 + in 2018
LINAC-4 | Protons | RF backgrounds and response to losses | Feb-April 2018
ORPHEE CEA/Saclay | Thermal neutrons | Response to thermal neutrons | 2018
Amande (CEA/Cadarache) | Mono-energetic neutrons | Efficiency studies. Different poly and convertors thickness | Feb or March 2018 (6days)
IPHI | Neutron production | Response study for different energies | From January 2018
Upssala + Saclay | Testing the ESS cryo- modules | Response to RF backgrounds | From January 2018
L. Segui 21/11/2017 – 4th ESS-BI Forum 7

## Slide 13: nBLM detectors distribution (I)
 | Detectors
MEBT | 4
DTL | 42
SPK | 26
L. Segui 21/11/2017 – 4th ESS-BI Forum 7
Fast
Slow
Irena and Thomas G. work

## Slide 14
 | Detectors
MEBT | 4
DTL | 42
SPK | 26
MB | 2
HB | 2
PBW | 6
Total | 82
nBLM detectors distribution (II)
L. Segui 21/11/2017 – 4th ESS-BI Forum 8
Irena and Thomas G. work

## Slide 15: nBLM detectors Integration in ess (I)
System of 82 detectors will be installed
  164 HV cables + 82 signal cables + 3x82 LV cables + gas lines
Detectors will be grouped for the gas lines and amplifiers low voltage cables
Two type of patch panels (2x6):
  Gas
  Cables connectors
Start design of detectors support
  Rail along linac
  Flexibility to move the detector in order to optimize the beam losses detection
Detectors in | Gas line | # of detectors
MEBT-DTL1 | Line 1 | 12
DTL2 | Line2 | 8
DTL3 | Line 3 | 8
DTL4 | Line4 | 8
DTL5 | Line 5 | 8
SPK1-4 | Line6 | 8
SPK5-8 | Line 7 | 8
SPK9-13 | Line8 | 10
MB-HB | Line 9 | 4
Bend Magnet | Line 10 | 6
L. Segui 21/11/2017 – 4th ESS-BI Forum 9

## Slide 16: nBLM detectors Integration in ess (II)
L. Segui 21/11/2017 – 4th ESS-BI Forum 10

## Slide 17: nBlm gas system
General design
The gas system consists in 3 parts:
  The bottle storage area outside the building
  Gas distribution system
    Distribution and return lines from (to) the rack to (from) the accelerator tunnel
    10 distribution + 10 return lines
  Gas Line system fo group of detectors
Gas bottle storage
Gas rack controller
Patch panels in Accelerator tunel
Each nBLM module
Exhaust
L. Segui 21/11/2017 – 4th ESS-BI Forum 11

## Slide 18: nBlm gas system
Micromegas are gaseous detectors. Work in circulation with open circuit
High reliable system for the 84 detectors
Gas | He + 10% CO2
Total flow | 10 - 20 l/h
Flow per line | 1-2 l/h
Pressure | 1atm
L. Segui 21/11/2017 – 4th ESS-BI Forum 12

## Slide 19: CONclusions
Since last BI Forum
  Initial tests with prototypes
   Design of new detectors
    Mechanics
    Electronics  Philippe’s talk
  PDR1.2 approved
  Fix distribution of detectors
  Start design of detectors supports and their integration in the linac
  Definition of analysis algorithm
  Specification of control system
  GUI development
Next months are critical to maintain schedule
  New detectors ready by beginning next year for full characterisation
  Finish cable definition for installation.
First tests with full acquisition system on-going
Integration of gas pipes design into model on-going  Thank you for the support from ESS!
L. Segui 21/11/2017 – 4th ESS-BI Forum 13
Yannick’s
talk

## Slide 20
Thomas
Papaevangelou,
Chef de Projet
Mariam Kebbiri
Détecteurs MicroMegas
Stephan Aune
System de Gaz
Détecteurs MicroMegas
Philippe Legou
Detector et
Front-End Electronics
Laura
Segui,
Post-doc
Caroline
Lahonde-Hamdoun
Détecteur
specialiste
Daniel
Desforge
Mechanical
Designer
Françoise
Gougnaud
Yannick Mariette
DIS
Tom Joannem
THANK YOU
Jacques Marroncle
ESS-I WP Diagnostics
Victor
Nadot
Quentin
Bertrand
Georgios
Tsiledakis,
Post-doc
Michel Combet
Front-End
Electronics
Pascal Le Bourlout
Front-End
Electronics
Olivier
Maillard
Front-End
Electronics
DEDIP

## Slide 21
BACK-UP

## Slide 22: Micromegas detectors
MicroMesh Gaseous Structures (Micromegas) are an improved amplification structure used to measure the ionized signal in a gaseous detector.
The detector consists on two parallel plates:
  a metallic micromesh suspended over an anode plane by insulator pillars
The device operates as a two-stage parallel plate avalanche chamber in two stage
  Conversion zone
  Amplification zone
30-150µm
To detect neutrons we need to place a convertor in the entrance of the conversion zone

## Slide 24: Studies by MC simulations
SLOW DETECTOR
Relative efficiency
Response time
Dependency with
  Moderator thickness
  MMs size
  B4C thickness
  Absorber thickness
Dependency with initial neutron energy
4 cm gives the most constant response over all range of energies
Dependency with moderator thickness
  ~5% detected in <1 µs for 4 cm
  Requirement by ESS 5 µs response in total, 3µs for detection and FEE
Dependency with initial neutron energy

## Slide 25: éTUDES PAR SIMULATION MC
SLOW DETECTOR
Gamma discrimination
Blind to gammas
Only sensitive to high energie gammas
With an energy threshold we can reject them
Thermal neutrons
  Energies between 0.01 and 1 eV
  Efficiency of < 0.007 % already with an energy deposited threshold of 10keV

## Slide 26: éTUDES PAR SIMULATION MC
FAST DETECTOR
100% events in <10 ns
Neutron initial entre
0.1eV et 100 MeV
Only sensitive to energies >0.5 MeV
Neutron efficiency
Initial neutrons from 0.1eV to 100 MeV
Time response:
just ToF, detector immediate response

## Slide 27: éTUDES PAR SIMULATION MC
FAST DETECTOR
Blind to gammas
Gamma discrimination

## Slide 28: nBlm gas system
Gas: He + 10% CO2
Flow: ~ 5 l/h, in recirculation
P ~ 1 atm
Volume/detector ~ 0.25 l
Leak tight and low outgassing
Gas bottle storage: 6-12 rack premix
  ~200 bar/bottle, 50 l 
  2 IN/2 OUT lines (1 in use, 1 spare)
  Outside gallery
From gas bottle to gas rack to patch panel to tunnel
  Distribute in 5 lines  one per DTL, in parallel
    5 IN/5 OUT Lines going to tunnel (+ spares)
  Electrovalve in/out in Klystron gallery
    Isolate system
  Flowmeter in/out in Klystron gallery
    Leak monitoring
Gas in serial for detectors in DTL
nBLM- PP-Gallery-
IN
OUT
Gas controller
Bottle rack
Designed by Stephan Aune
Serial
Serial and shunt?

## Slide 29
MEBT
DTL-1
DTL-2
IN line
OUT line
Detail of one nBLM gas distribution patch-panel
Flexibles
Shielding wall
Note only the slow draw
nBLM detectors Integration in ess (III)