## Slide 1: Bunker Project Purchasing/Manufacturing
www.europeanspallationsource.se
5 december 2017
Zvonko L. Mirko M.

## Slide 2: The Bunker Purchasing/Manufacturing content
Purchasing
  Prequalification Tender
  Procurement Tender
Manufacturing
  Planned setup

## Slide 3: Purchasing – stage I
Cold box arrival to ESS
Tendering plan
Stage I:
This is the pre-qualification stage.
In this stage we will select a number of companies who pass this gate; and issue ‘turn key’ procurement tender to those qualified companies.
The pre-qualification criteria center around ensuring the supplier has:
required turnover,
has required background demonstrating ability to deliver this project and,
can demonstrate that the proposed contract layout can be delivered.
Proposed contract setup is broadly explained; being an ‘open book’ project, with heavy reliance on collaboration.
The collaboration model will be set up by the supplier and ESS, ensuring the network of companies involved in production of the bunker is included.
Notes: The NBPI is still in the design phase so operational and maintenance aspects are in the same state.
Based on this reasoning - each NBPI is expected to be changed every 15 years. When we are up and running with all 42 ports this will mean a change of approximately three beam guides each year.
Port block surface is refurbished due to potential damage from NBW

## Slide 4: Purchasing – stage II
Cold box arrival to ESS
Tendering plan
Stage II:
This project will be manages as an open book contract,
We will set-up collaborative relationship with the supplier and execute the production, pre-assembly and installation together,
The difference between this and other projects, is that for this project we will deliver the detailed design, but in the model form only (we will supply detail drawings only of key components and subassemblies to enable us to perform the budgeting work safely),
The selection criteria for this tendering process will center around company’ ability to engage into collaborative environment, and the expected fees.
Notes: The NBPI is still in the design phase so operational and maintenance aspects are in the same state.
Based on this reasoning - each NBPI is expected to be changed every 15 years. When we are up and running with all 42 ports this will mean a change of approximately three beam guides each year.
Port block surface is refurbished due to potential damage from NBW

## Slide 5
Procurement/Tendering schedule
Mirko M.
Estimated date | Activity
2017-11-16 | Contract published on the ESS website. Tendering documents made available to the potential candidates.
2017-11-30 | Deadline for submitting requests for clarification to ESS.
2017-12-11 | Deadline for submission of PQQ.
2017-12-22 | Notification of the result of the pre-qualification sent to the candidates (selection of max 5 candidates).
2018-01-31 | Invitation to Tender (ITT) issued to selected candidates
2018-03-05 | Deadline for submission of Tenders
2018-03-30 | Notification of the award and the evaluation results sent to the tenderers
2018-04-09 | Contract signed
Apr 2018 – Aug 2018 | Design review + ESS approval of any changes, ordering of materials
Sep 2018 – July 2020 | Delivery and Construction

## Slide 6: Manufacturing plan
Cold box arrival to ESS
The project structure could look something like this:
Supplier – manages ‘production office’ (houses bunker production project personnel, drafting personnel, ESS engineer will be seated at this office; alternatively, a production manager/engineer is located at ESS-Lund; calls for any ‘open book contract’ discussions)
*This office is responsible for ordering all materials (whether the materials are pre-cut to final shapes, or delivered raw and cut at the supplier’ facility, is up to the supplier), production of detailed drawings, managing logistics and assembly of individual blocks; manages delivery of
ESS bunker office – oversees the drafting and production effort. Enables collaboration model to work (ensures communication is maintained, key milestones are reviewed, and calls for any discussions relating to managing the open book contract).
Notes: The NBPI is still in the design phase so operational and maintenance aspects are in the same state.
Based on this reasoning - each NBPI is expected to be changed every 15 years. When we are up and running with all 42 ports this will mean a change of approximately three beam guides each year.
Port block surface is refurbished due to potential damage from NBW

## Slide 7: Project & Manufacturing plan
Project office
QA handling
Logistics
Sequencing
(Integrator engineer)
Project office
Manufacturing office
Design office
(ESS engineer)
ESS bunker office
Integrator
Supplier 1 [HDPE…]
Supplier 2 [steel…]
Supplier 3 [concrete…
Open book project
Cash flow monitored
Early detection of possible issues
Logistics coordinated between ESS and the Integrator
Notes: The NBPI is still in the design phase so operational and maintenance aspects are in the same state.
Based on this reasoning - each NBPI is expected to be changed every 15 years. When we are up and running with all 42 ports this will mean a change of approximately three beam guides each year.
Port block surface is refurbished due to potential damage from NBW

## Slide 8: Project & Manufacturing plan
Project office
QA handling
Logistics
Sequencing
(Integrator engineer)
Project office
Manufacturing office
Design office
(ESS engineer)
ESS bunker office
Integrator
Supplier 1 [HDPE…]
Supplier 2 [steel…]
Supplier 3 [concrete…
Contract signed
Design review and translation
Early detection of possible issues
Logistics coordinated between ESS and the Integrator
Commence generating manufacturing documentation
Cash flow monitored
Early detection of possible issues
Logistics coordinated between ESS and the Integrator
Notes: The NBPI is still in the design phase so operational and maintenance aspects are in the same state.
Based on this reasoning - each NBPI is expected to be changed every 15 years. When we are up and running with all 42 ports this will mean a change of approximately three beam guides each year.
Port block surface is refurbished due to potential damage from NBW

## Slide 9
2018 |  |  |  | 2019 |  |  |  | 2020 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Procur.
Colaboration setup
Assembly; logistics; Installation I
Manufacturing documentation
Order & Production of raw materials
HDPE & HDPE+B (pressing)
Steel (sourcing required stock_logistics)
High level Bunker manufacturing and Installation Schedule
Sofie O.
HDPE & HDPE+B final machining
Steel final machining
Temporary shielding production & delivery
Bunker frame production

## Slide 10
2018 |  |  |  | 2019 |  |  |  | 2020 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Procur.
Colab. setup
Production (confirmed with potential supplier) i
Frame
Roof elements and subassemblies
Wall elements and subassemblies
Temporary shielding
Installation (detailed schedule presented by ABi)
LOGISTICS
Predrilling
Frame and base plates
Walls
Roof
Utilities
PSS
High level Bunker manufacturing and Installation Schedule
Sofie O.

## Slide 11
R6
(Jan 2019)
LS & Insert (with Target)
installation
(Feb-Sep 2019)
Bunker Pillars
& Beams
(June-Oct 2019)
Bunker walls & first roof layer
(Aug-Nov 2019)
Instrument & TBL installation
(Nov 2019 – May 2020 )
Bunker roof
outer layer
(June-Aug 2020)
Utilities/Infrastr. & ICS installation & test
(Sep-Oct 2020)
Beam on Target
Oct 2020
First neutron instruments planning for “In-Bunker” installation within this 6 month period.
High level Bunker manufacturing and Installation Schedule
Installations assumes normal working hours and summer/Christmas holidays
Sofie O.
Critical Design Review Dec 2017
Contract for manufacturing Q1 2018
First Delivery to ESS site (R6 & steel sructure) Dec 2018
Mid delivery to ESS site (wall blocks & first roof layer) June 2019
Final delivery to ESS site (final roof layer) July 2020

## Slide 12: The Bunker Q/A
End of presentation
Q/A