## Slide 1: Technical challenges for a green field facility like ESS
Roland Garoby
Technical Director
www.europeanspallationsource.se
19 January 2018

## Slide 2
ESS goals and planning
Technical challenges during the successive project phases:
  Conceptual Design
  Design Update
  Detailed Design and Construction
  Installation and commissioning
ESS experience working with in-kind contributions
Summary

## Slide 3: ESS goals and constraints
ESS shall be a spallation neutron source based on a pulsed proton accelerator
Goals
  15 public instruments at end of construction
  Record neutron brilliance (>30 times ILL)
  5 MW ultimate proton beam power*
  “Sustainability”:
    Energy responsible (Yearly consumption < 270 GWh)
    Renewable energy
    Recyclable heat
  Large fraction of “in-kind” (>60% excl. CF)
Constraints
  Safety & Environment objectives
  Cost
  Schedule
World top
performance
World
reference
*starting at 2 MW in 2023
  ESS Mission:
  design, build, and operate
  the world’s leading
  research facility using neutrons

## Slide 4: From a Green Field in 2009 to a World-leading facility in 2025…
2014
Construction Starts on Green Field Site
2009
Decision to Site ESS in Lund
2025
ESS Construction Phase Complete
2003
European Design of ESS Completed
2012
ESS Design Update Phase Complete
2021
Machine Ready for
Beam on Target
2023
ESS Starts
User Program

## Slide 5: ESS financing
Host Countries Sweden and Denmark
Construction 47.5% Cash Investment ~ 97%
Operations 15%
Non Host Member Countries
Construction 52.5% In-kind Deliverables ~ 70%
Operations 85% (Goal)
(Jan 2013 pricing) | M €
Conventional Facilities | 531.9
Extra CF investment by host countries | -93.0
Accelerator Systems | 510.2
Target Systems | 155.2
Integrated Control System | 73.0
Design & Engineering | 33.7
Neutron Scattering Systems | 350.0
Project Support & Administration and Licensing | 123.8
Contingency | 158.2
Total Construction Budget | 1843.0

## Slide 6
ESS goals and planning
Technical challenges during the successive project phases:
  Conceptual Design
  Design Update
  Detailed Design and Construction
  Installation and commissioning
ESS experience working with in-kind contributions
Summary

## Slide 7: Conceptual Design
Goals:
  To outline the design of a facility that meets the users’ requirements for world-leading performance in ~15 years,
  To prepare a project proposal with a planning and a budget.
Challenges:
  Need for adequate amount of expert technical competencies covering a wide spectrum
  Estimating budget for utilities & infrastructure
Solutions:
  Aggressive recruitment
  Extensive use of previous projects’ proposals
  Extensive call for international expertize
Issues:
  Gaps in spectrum of required in-house competencies
  Difficulty getting good quality requirements for utilities & infrastructure
  Difficulty estimating budget and planning for an organization without similar previous experience
  Underestimation of resources required for managing in-kind and for licensing
Possibility to recruit world-wide
Flexibility in employment conditions
Set-up collaborations with existing institutions
Co-fund some developments and prototypes in these labs.
Initial requirements

## Slide 8: Design Update
Goals:
  To refine the design of the facility and its components and reduce cost,
  To define the project baseline in detail (WBS, Milestones, Cost book...)
Challenges:
  Need for adequate amount of competencies covering the whole spectrum of construction activities
Solutions:
  Aggressive recruitment
  Involve institutions interested to contribute in-kind to construction
  Extensive call for international expertize
  Allocate responsibilities for utilities & infrastructure
Issues:
  Gaps in spectrum of required in-house competencies
  Risk of “Conflict of interest” at in-kind partners…
  Diversity of approaches to problem-solving due to diversity of professional backgrounds
  Standardization of Engineering tools
Partner countries willing to contribute to construction
Additional requirements
Strong and consistent management

## Slide 9: Detailed Design & Construction
Goals:
  To split between internal and in-kind work packages,
  To negotiate and sign contracts with industry and in-kind partners
  To run the contracts for building the facility and all its components
Challenges:
  Set-up and run a continuously growing/changing project organization
  Freeze design(!) and control change
  Provide “good enough” requirements for Conventional Facility construction
  Define “Interface Requirements”
  Negotiate and run contracts with multiple in-kind partners
  Build state-of-the-art equipment on-time and on-budget
  Quality insurance and control
Solutions:
  Set-up a project organization and adjust it as it grows and as problems arise…
  Enforce Configuration Control and Quality Control
  Impose standard software tools, including at in-kind partners…
  Contract state-of-the-art equipment to expert in-kind partners
  Technical Boards, Collaboration Boards and Reviews (PDR, CDR, IRR, TRR, SRR)
Additional requirements
Dedicated staff
Strenghtened management and engineering practice

## Slide 10: Installation and commissioning
Goals:
  To install and test equipment,
  To progressively commission the facility
Challenges:
  Ensure safety on site while executing all the necessary tasks
  Quality control
  Logistics with possibility of storage of delivered equipment
  Coordination of installation activities
  Management and/or support to workers (employees, industry, in-kind partners…)
  Get necessary licenses from host state authorities
  Operate and maintain technical infrastructure equipment when delivered
Solutions:
  Adapt the project organization by superimposing an installation structure with some new functions and adding support teams for utilities & infrastructure
  Set-up a RATS (Reception, Acceptance, Test and Storage) facility
  Implement an EAM tool (Enterprise Asset Management)
  Organize the preparation of the successive permit applications as projects
Additional requirements
Strong safety team

## Slide 11
ESS goals and planning
Technical challenges during the successive project phases:
  Conceptual Design
  Design Update
  Detailed Design and Construction
  Installation and commissioning
ESS experience working with in-kind contributions
Summary

## Slide 12: ESS in-kind contributions - General principles -
Potential in-kind contributions are defined by the ESS Programme Plan
Values based on ESS Cost Book
Each contract to follow a pre-defined structure
The delivering party is wholly responsible for the contribution (technical, financial, commercial)
In-Kind Review Committee to evaluate all IKC agreement proposals
ESS Council to approve all in-kind contracts
Based on final evaluation the Member Country gets accredited the value of the In-Kind Contribution.
Governing documents
Framework for handling In-Kind Contributions
IKC Agreement template
IKC Agreement Schedule template
IKC Management Plan

## Slide 13: ESS in-kind contributions - Contract structure -
“Framework for handling In-Kind Contributions” defines minimum content
Schedule 2
Schedule 1
Deliverables
Time schedule and delivery of project
Reporting
Excluded background
Legal and commercial terms and conditions
Definitions
Work programmes
Obligations
Organization
…
…
…
Etc.
Schedule X
Framework for handling In-Kind Contributions
IKC Agreement structure:
1. General Terms and conditions (signed only once with each contributing partner)
2. Framework for handling in-kind contributions
3. Schedules (Technical Annex, separately added for each WP or group of WPs)
in General Terms and Conditions already covered:
Work programme definition
Obligations of the partner / ESS (standard of performance, compliance with laws, conflicts of interest, communication, decisions, approvals)
Organization
Delivery of project results (evaluation, handling of delays and defects)
Handling/managing variations
Transportation
Transfer of ownership
Financial matters
Liability
Intellectual property rights and confidentiality (ownership of background/foreground, access rights)
Force Majeure
Duration and Termination
Miscellaneous (secondment within WP, subcontracting, amendments, waiver, publicity)
Settlement of disputes

## Slide 14: ESS In-kind contributions - In-Kind process -
PHASE 3
PHASE 2
PHASE 1
ESS Programme Plan
WPs/WU 1
WPs/WU 2
WPs/WU 3
WPs/WU 4
EOI
response
ESS + Potential party discussion
Contract proposal
IKRC recommendation + Council approval
IKC frame contract + technical annex
Detailed Design Phase
ESS + Partner Critical Design Review (CDR)
Realization and Verification
ESS + Partner
System Acceptance Review (SAR)
IKRC + Council approval
Transfer of ownership
IKC value crediting to member country

## Slide 15: ESS In-kind contributions - Structure of Schedule (“Technical Annex”)-
Scope
SoW definition
Related documents
Applicable documents
Reference documents
Terms and definitions
Abbreviations
Definitions
Project definition
Deliverables, deadlines – as defined in Programme plan
Value as defined in Cost Book
Project stages 1. Design Phase 2. Realization and verification phase
Project schedule and key milestones
Deliverables (Status reports, Data packages)
Tasks applicable to project stages
Project management and control through milestones
Risk management
Configuration management
Organization
WU coordinators from both parties
Product and quality assurance, Safety
Applicable law, legislation and standards
Quality plan
Documentation format
Language, file formats
Transportation and delivery
DDP by default
Warranty
Warranty requirements
Excluded background
In accordance with the main Agreement

## Slide 16: ESS partners
Aarhus University
Atomki - Institute for Nuclear Research
Bergen University
CEA Saclay, Paris
Centre for Energy Research, Budapest
Centre for Nuclear Research, Poland, (NCBJ)
CNR, Rome
CNRS Orsay, Paris
Cockcroft Institute, Daresbury
Elettra – Sincrotrone Trieste
ESS Bilbao
Forschungszentrum Jülich
Helmholtz-Zentrum Geesthacht
Huddersfield University
IFJ PAN, Krakow
INFN, Catania
INFN, Legnaro
INFN, Milan
Institute for Energy Research (IFE)
Rutherford-Appleton
Laboratory, Oxford(ISIS)
Kopenhagen University
Laboratoire Léon Brilouin (CEA – CNRS – LLB)
Lund University
Nuclear Physics Institute of the ASCR
Oslo University
Paul Scherrer Institute (PSI)
Polska Grupa Energetyczna - PGE
Roskilde University
Tallinn Technical University
Technical University of Denmark
Technical University Munich
Science and Technology Facilities Council
UKAEA Culham
University of Tartu
Uppsala University
WIGNER Research Centre for Physics
Wroclaw University of Technology
Warsaw University of Technology
Zurich University of Applied Sciences (ZHAW)
>110 Technical Annexes signed as of December 2017…

## Slide 17: Year by Year In-Kind planning
Chart: Estimated value of in-kind contributions
| End of 2014 | End of 2015 | End of 2016 | End of 2017 [forecast] | Mid 2018 [estimates]
Signed TA | 0.19 | 128.5 | 254.7 | 323.44 | 470
Planned | 272.59 | 207.15 | 258.49 | 215.34 | 50
Potential | 335.78 | 313.19 | 110.54 | 25
Collaborations | 9.4 | 16.7 | 17.09 | 22 | 30
Notes: Some notes:
The total In-Kind goes up between 2014 and 2015 since ESS was not done with identifying In-Kind opportunities in that period. After that, the total In-Kind value decreases linearly.
The values of potential and planned decrease linearly. End of 2016 sees a number of Instruments moving to planned, therefore potential reducing significantly, while planned reducing only by 50M€
The end of 2017 is forecasted through using XRM+ data, but also discussions with Michela. The basis for 435 number is current status of everything agreed (be it TA w/ cover page or full IKA) – 286M€ + 70-80% of instrument TAs signed + pretty much all other remaining packages.
Mid 2018 is the estimate which relies on end of 2017 forecast. If we sign all of Instrument TAs but one, or maybe two, and with a small number of lower value packages, the total In-Kind should get to around 525-545M€ mark, with around 470M€ agreed. By the end of 2018 everything should be agreed.

## Slide 18: Lessons learnt working with in-kind contributions – [1 of 5]
ESS specific situation
  In-kind goals were set “top-down” at ambitious levels early in the negotiation with potential member countries and when ESS had few employees. That had the following consequences:
    Early involvement of institutions interested in providing in-kind at a time when the ESS team was still small gave them the possibility to guide decisions and estimates (mentioned as “Risk of conflict of interest “in slide 8…)
    Intense effort by ESS to reach these goals ending with some contracts being simply transfer of procurements…

## Slide 19: Lessons learnt working with in-kind contributions – [2 of 5]
Contract negotiations (1)
  Potential in-kind partners are only interested in work packages with high technology
    Allocate work-package(s) matching the competences of the in-kind partner
    Foresee from the start enough internal resources [Technical as well as Administrative (procurement, legal, logistics, storage…)] to self-perform “low tech” work packages
  All partners are different:
    Foresee large workload/multiple travels & meetings/long duration (year(s))
    Recruit dedicated staff
    Better coordination inside the partner countries is necessary to accelerate the process and increase efficiency
    Governing documents and templates approved by Council should not be negotiable
  It is more efficient for ESS to take care locally of some work/subcontracts, even if they should logically be part of some in-kind contributions:
    Set-up a common fund subsidized in cash by in-kind partners

## Slide 20: Lessons learnt working with in-kind contributions – [3 of 5]
Contract negotiations (2)
  Include all conditions in the initial contract: technical standards for design, documentation and reporting, safety requirements, CE conformity…
    Decide early on standards, safety rules, CE conformity, publish Engineering Handbook…
  Interactions are at multiple levels: Technical partners/Country leading institution/Ministry
    Organize fluid communication on IK subjects inside the organization to be able to trigger action quickly
  Getting VAT exemption for in-kind contributions is very complex for an ERIC
    Improve ERIC statute (e.g. stating that countries contributions are recorded at the their value without VAT)…

## Slide 21: Lessons learnt working with in-kind contributions – [4 of 5]
Contract negotiations (3)
  In-kind partners are hostile to owning risks, contrary to the spirit and terms for in-kind contributions as stated by the Council
    Governing documents and templates approved by Council should not be negotiable
    Crucial difference between “Partnership” and usual commercial relations
  In-kind partners are reluctant to/cannot accept penalties in case of delay or other problems
    Crucial difference between “Partnership” and usual commercial relations
    Escalate issues at country government level as they happen

## Slide 22: Lessons working with in-kind contributions – [5 of 5]
Contract execution
  Need for frequent and detailed interactions and reporting
    Set-up regular/frequent meetings at all levels
    Implement Technical Boards and Collaboration Boards
  Need for an authority overseeing the progress of in-kind work and reporting directly to the Council
    Extension of mandate of In-Kind Review Committee
  Difficult/time consuming/inefficient to reduce scope after contract signature
    Avoid trying to renegotiate
  On-site work (installation, test, commissioning) requires fulfilling a significant amount of administrative formalities with the host country authorities
    Plan for it in advance

## Slide 23
ESS goals and planning
Technical challenges during the successive project phases:
  Conceptual Design
  Design Update
  Detailed Design and Construction
  Installation and commissioning
ESS experience working with in-kind contributions
Summary

## Slide 24: Summary
ESS is a typical example of a large size / world class scientific facility built in a green field.
ESS construction is 40% complete and a number of important lessons have already been learnt.
Relying extensively on in-kind contributions is nowadays a requirement from stakeholders. It gives access to the competences of experienced laboratories but it requires significant in-house resources and it is especially challenging for a “green-field” facility. ESS practice demonstrates that using it at a large scale in Europe requires improvements…

## Slide 25
Thank you
for your attention!