## Slide 1: PREMP update
Malcolm Guthrie
www.europeanspallationsource.se
2 March, 2018

## Slide 2: Sample Environment Suite for PREMP

## Slide 3: Sample Environment Suite for PREMP
Focus on construction project
Trigger instrument – first to require SES
Typically requested for cold commissioning
All trigger instruments are in Long Hall
Notes: Raman 41.6k (could de-scope to ruby only) ~ 15k (saving 26k)
Portable laser 100k (could swap for MP SEE).
Corrosive gas already removed. 15k

## Slide 4: Rebaselining
Impacts - (Provisional!)
Long Hall
Cold comm. delay ~ 4 months
Hot comm. delay ~ 10 months
D03
12-18 months cold comm. delay
D01
12 months cold comm. delay

## Slide 5: Schedule example: PE systems
Prelim. design
Detailed. design
Procurement, integration,
certification
Cold comm.
Hot comm.
Generic:
ready
Schedule 2017
Detailed. design
Procurement, integration,
certification
Cold comm.
Hot comm.
Installation, cold comm.
18
19
20
21
22
23
Hot comm.
Proc./Mfg
Det. Des.
ops.
Access E03/E02
MAGIC (trig)
BOT
PE

## Slide 6: Schedule example: PE systems
Prelim. design
Detailed. design
Procurement, integration,
certification
Cold comm.
Hot comm.
Generic:
ready
Schedule 2017
Detailed. design
Procurement, integration,
certification
Cold comm.
Hot comm.
Installation, cold comm.
18
19
20
21
22
23
Hot comm.
Proc./Mfg
Det. Des.
ops.
Access E03/E02
Det. Design
MAGIC (trig)
Proc.
Installation
Cold
hot
SES project steps:
Installation: control systems, safety, trainining, certification (CE-marking),
Cold comm: Checking system integrates with instrument
Hot comm: testing background, collimation, shielding
PE SES
Sign TA
w/ LLB
BOT
PE

## Slide 7: Schedule example: PE systems
Prelim. design
Detailed. design
Procurement, integration,
certification
Cold comm.
Hot comm.
Generic:
ready
Schedule 2018 (Provisional!)
Detailed. design
Procurement, integration,
certification
Cold comm.
Hot comm.
Installation, cold comm.
18
19
20
21
22
23
Hot
Proc./Mfg
Det. Des.
ops.
Access E03
Det. Design
MAGIC (trig)
Proc.
Installation
Cold
hot
PE SES
Sign TA
w/ LLB
BOT
Full Access E02
Part. Access E02
PE
No significant change in delivery
Extended period for installation cold comm.
Very rushed hot comm.
Strategy may be hot-commissioning activities at other spallation sources

## Slide 8: Update preMP
Inst specific BEER not yet progressed (2019)
  €300k for stress rig
  No clear strategy yet for remaining €300k in budget
    stir welding (€200k) dilatometer (€400k)
  Chalmers furnace project started (PD hired)
Non inst—specific.
  Recognise need to expand Pool (need IK partner or collaborator!)
  €40k “Generic stress-strain rig”. Do we want it? Should start project in 2018. Who is potential IK partner?
  Other items (Equip list for OPS and external funds)
  Upcoming Nordforsk meeting (2-3 May, Denmark)
  http://chem.au.dk/en/research/conferences-and-workshops/neutron-and-synchrotron-sample-environment-workshop/
Advice:
  €100k for portable laser heating could be re-directed to MP.

## Slide 9: Update PREmp
Held community workshop in Lund (July 2017)
  Broadly sanctioned pressure plan
  Highlighted need for a <5 GPa <1K cell
  Highlighted need for >= 0.7 GPa liquid cell
Preliminary design finished for most SES
Close to finalising agreement on LLB IK deal
Clear priority to focus on safety and quality (CE-marking) for high-pressure SES.

## Slide 10: Activities 2018 – Continued DAC advances
“Day 1 target science”
  diffraction: light molecular systems D2O,ND3,CD4 ; superconductors; magnetism
  Spectroscopy: exotic quasiparticles, superconductivity
  SANS*: polymers, food science, high press biology
Angström cluster proposal for “SANS DAC”
New cells have large aperture enabling SXL diffraction and wider Q-range. And internal clamp system for low T
Powder diffraction now possible up to 60 GPa

## Slide 11: Activities 2018 - LLB IK
Primarily establishing baseline capabilities:
7kbar gas (and liquid?)
2 GPa clamp
20 GPa PE cells (standard anvils)
  Anvil development separate
Also gas loading (for PE and smaller cells)
And specialised cryostat for P cells (spec not fixed)

## Slide 12: Activities in 2018
Quality – Safety
  Define requirements for CE marking (metallurgy, testing, safety factor, calculations…)
  Develop safety (risk assessement, training, integration inc control software)
Based around V3 Paris-Edinburgh press & hydraulic system